## Project Planner
| Time Plan | [6 empty] | Plan Duration |  |  |  |  | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan) | [7 empty] | Plan Duration |  |  |  |  | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan) | [7 empty] | Plan Duration |  |  |  |  | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan) | [7 empty] | Plan Duration |  |  |  |  | Actual Start |  |  |  |  | % Complete |  |  | Actual (beyond plan) | % Complete (beyond plan)
| Start Date: 25th Jan, 2020 | Revisited: 1st Mar,2020
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | W1 - HOLIDAY | [6 empty] | W2 - HOLIDAY | [6 empty] | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98
1 | Survey Raspberry Pi features, pricing and availability in market | 1 | 5 | 1 | 6 | 100%
2 | Document conclusion of survey | 6 | 2 | 6 | 2 | 100%
3 | Determine the required relay module | 7 | 3 | 8 | 3 | 100%
4 | Design hardware setup | 10 | 4 | 11 | 4 | 100%
5 | End of Mid-Year Holiday
6 | Test hardware setup | 15 | 30 | 15 | 30 | 85%
7 | Improve hardware design | 20 | 25 | 20 | 25 | 55%
8 | Test connectivity of hardware setup (performance) | 41 | 7 | 32 | 20 | 10%
9 | Design and document test cases (Chapter 3: Theory) | 44 | 20 | - | - | 0%
10 | Midterm Exams | 64 | 7
11 | Develop test cases (software) | 71 | 10 | - | - | 0%
12 | Further research test cases techniques | 75 | 5 | - | - | 0%
13 | Optimize test cases (software) | 78 | 10 | - | - | 0%
14 | Document implementation and conclusion (Chapter 4,5: Implementation, Conclusion) | 83 | 14 | - | - | 0%
Activities are subject to expansion or extension within upcoming revisits.